## GTM Plan - By Due (2)
Phase | Project | Project Type | Customer Facing | Segment- specific | Dept. Owner | Individual Owner | Exec Stakeholder | Work Start Date | Completion / Launch Date | Status | Notes | Launch Status | Count
P1: Strategy & Plan (Pre-launch) | GTM Plan Development | Strategy |  |  | Marketing | PMM Lead | VP Marketing | 2026-01-05 | 2026-01-15 | COMPLETE | Align scope, audiences, launch goals and decision owners | COMPLETE
| Market Opportunity & Category Review | Research |  |  | Marketing | Market Insights | VP Marketing | 2026-01-05 | 2026-01-19 | COMPLETE | Size priority use cases and validate category dynamics | In Progress
| Competitive Analysis | Research |  |  | Marketing | PMM Lead | VP Marketing | 2026-01-05 | 2026-01-23 | COMPLETE | Compare platform, point-solution and status-quo alternatives | Not Started
| Validate ICP & Buyer Personas | Strategy |  | X | Marketing | PMM Lead | CRO | 2026-01-08 | 2026-01-26 | COMPLETE | Validate Operations, IT and Finance buying roles | At Risk
| Launch Goals & KPI Definition | Strategy |  |  | Marketing | Marketing Ops | VP Marketing | 2026-01-10 | 2026-01-23 | COMPLETE | Define adoption, pipeline, conversion and expansion measures
| Budget Allocation | Strategy |  |  | Marketing | Demand Gen Lead | VP Marketing | 2026-01-13 | 2026-01-30 | In Progress | Allocate across content, paid, events and customer programs
| Messaging & Positioning | Strategy |  |  | Marketing | PMM Lead | VP Marketing | 2026-01-13 | 2026-01-29 | COMPLETE | Core company, product and segment messaging
| Value Proposition | Strategy |  |  | Marketing | PMM Lead | VP Marketing | 2026-01-13 | 2026-01-29 | COMPLETE | Tie workflow automation to speed, visibility and lower operating friction
| Priority Use Cases | Strategy |  | X | Marketing | PMM Lead | VP Product | 2026-01-15 | 2026-02-02 | In Progress | Employee onboarding, approvals, customer handoffs and recurring operations
| Pricing & Packaging Review | Strategy |  | X | Product/Finance | Product Lead | CFO | 2026-01-19 | 2026-02-09 | In Progress | Validate tiers, packaging logic and expansion path
| Customer Validation Interviews | Research |  | X | Marketing/Product | Research Lead | VP Product | 2026-01-19 | 2026-02-12 | In Progress | Test problem language, proof points and willingness to change
| Launch Readiness Review | Strategy |  |  | Cross-functional | GTM Lead | CEO | 2026-02-09 | 2026-02-16 | Not Started | Confirm product, support, sales and marketing readiness
P2: Launch Readiness & Activation (Launch) | Product Naming & Narrative | Marketing - Content | X |  | Marketing | PMM Lead | VP Marketing | 2026-01-30 | 2026-02-19 | In Progress | Finalize launch narrative and product naming
| Product Overview Datasheet | Marketing - Content | X |  | Marketing | Content Lead | VP Marketing | 2026-02-04 | 2026-02-24 | Not Started | One-page overview for buyers and sellers
| Use-Case Datasheets | Marketing - Content | X | X | Marketing | Content Lead | VP Marketing | 2026-02-06 | 2026-03-01 | Not Started | Create modular assets for priority workflows
| Sales Deck | Sales Support | X |  | Marketing | PMM Lead | CRO | 2026-02-09 | 2026-03-02 | Not Started | Problem, value, proof, use cases and next step
| Sales Training Materials | Sales Prep |  |  | Marketing | PMM Lead | CRO | 2026-02-12 | 2026-03-04 | Not Started | Discovery guide, demo story and objection handling
| Competitive Battlecards | Sales Support |  |  | Marketing | PMM Lead | CRO | 2026-02-12 | 2026-03-06 | Not Started | Position against suites, point tools and status quo
| Sales Training & Certification | Sales Prep |  |  | Sales/Marketing | Enablement Lead | CRO | 2026-02-26 | 2026-03-11 | Not Started | Role-play discovery, positioning and demo flow
| BDR / SDR Playbook | Marketing - Outreach | X | X | Sales/Marketing | Demand Gen Lead | CRO | 2026-02-16 | 2026-03-08 | Not Started | Triggers, sequences, talk tracks and qualification
| Product Web Page | Marketing - Content | X |  | Marketing | Web Lead | VP Marketing | 2026-02-14 | 2026-03-09 | Not Started | Primary launch destination
| Use-Case Landing Pages | Marketing - Content | X | X | Marketing | Web Lead | VP Marketing | 2026-02-16 | 2026-03-12 | Not Started | Pages for Operations and IT-led scenarios
| FAQ | Marketing - Content | X |  | Marketing | PMM Lead | VP Product | 2026-02-19 | 2026-03-10 | Not Started | Buyer, admin, security and implementation questions
| Launch Webinar | Marketing - Content | X |  | Marketing | Content Lead | VP Marketing | 2026-02-22 | 2026-03-18 | Not Started | Educational launch event with live product story
| Launch Email 1 | Marketing - Outreach | X | X | Marketing | Lifecycle Lead | VP Marketing | 2026-03-04 | 2026-03-16 | Not Started | Problem / category framing
| Launch Blog Post | Marketing - Content | X |  | Marketing | Content Lead | VP Marketing | 2026-03-01 | 2026-03-16 | Not Started | Point of view on scaling operations without complexity
| Paid Search Campaign | Marketing - Outreach | X | X | Marketing | Demand Gen Lead | VP Marketing | 2026-03-01 | 2026-03-19 | Not Started | High-intent workflow automation terms
| Retargeting Campaign | Marketing - Outreach | X |  | Marketing | Demand Gen Lead | VP Marketing | 2026-03-06 | 2026-03-21 | Not Started | Re-engage launch-page and content visitors
| LinkedIn Campaign | Marketing - Outreach | X | X | Marketing | Demand Gen Lead | VP Marketing | 2026-03-04 | 2026-03-21 | Not Started | Operations and IT audience campaigns
| Launch Email 2 | Marketing - Outreach | X | X | Marketing | Lifecycle Lead | VP Marketing | 2026-03-18 | 2026-03-28 | Not Started | Use-case and proof-point follow-up
| Executive Guide / eBook | Marketing - Content | X |  | Marketing | Content Lead | VP Marketing | 2026-02-22 | 2026-03-31 | Not Started | Guide to eliminating operational friction as companies scale
| Customer / Admin Onboarding Assets | Onboarding | X |  | Customer Success | CS Enablement | VP Customer | 2026-02-26 | 2026-03-24 | Not Started | Quick start, admin setup and adoption resources
| Product Development & QA | Development |  |  | Product/Eng | Product Lead | VP Product | 2026-01-06 | 2026-03-22 | In Progress | Final feature hardening, analytics and integration testing
| General Availability Launch | Launch | X |  | Cross-functional | GTM Lead | CEO | 2026-03-23 | 2026-03-23 | Not Started | Public launch
| Product Demo Video | Marketing - Content | X |  | Marketing | Video / Content | VP Marketing | 2026-03-01 | 2026-03-20 | Not Started | 90-second overview plus modular feature clips
| Analyst / Influencer Briefings | PR / AR | X |  | Marketing | Comms Lead | VP Marketing | 2026-03-04 | 2026-03-22 | Not Started | Brief relevant category voices under embargo
P3: Tracking & Optimization (Post-launch) | Sales Win/Loss Review | Tracking |  |  | Marketing/Sales | PMM Lead | CRO | 2026-03-31 | 2026-04-30 | Not Started | Identify message, product and competitive patterns
| Product Analytics Dashboard | Tracking |  |  | Product | Product Analytics | VP Product | 2026-03-23 | 2026-04-07 | Not Started | Activation, feature adoption, retention and workflow completion
| Customer Feedback Program | Tracking |  |  | Customer Success | Customer Insights | VP Customer | 2026-03-28 | 2026-04-25 | Not Started | Structured feedback from admins, users and buyers
| Pipeline & Funnel Review | Tracking |  |  | Marketing/Sales | Marketing Ops | VP Marketing | 2026-03-30 | 2026-04-20 | Not Started | Review source, conversion, velocity and segment performance
| Adjust Messaging & Assets | Strategy | X | X | Marketing | PMM Lead | VP Marketing | 2026-04-20 | 2026-05-10 | Not Started | Refine based on customer language and sales evidence
| Roadmap Input & Prioritization | Strategy |  |  | Product/Eng | Product Lead | VP Product | 2026-04-20 | 2026-05-15 | Not Started | Feed launch learnings into roadmap decisions
| Customer Testimonials | Marketing - Content | X |  | Marketing/CS | Customer Marketing | VP Marketing | 2026-04-20 | 2026-05-20 | Not Started | Capture credible proof from early adopters
| Reference & Advocacy Program | Marketing - Content | X |  | Marketing/CS | Customer Marketing | VP Customer | 2026-04-30 | 2026-05-30 | Not Started | Develop reference pool and advocacy motions
| Customer Case Study | Marketing - Content | X | X | Marketing | Content Lead | VP Marketing | 2026-05-10 | 2026-06-09 | Not Started | Document measurable before/after business impact
PUBLIC PORTFOLIO EXAMPLE — Fictional company, product, owners, dates, claims and launch details. Framework illustrates GTM planning methodology only.

## Template
Phase | Project | Project Type | Customer Facing | Segment- specific | Dept. Owner | Individual Owner | Exec Stakeholder | Work Start Date | Completion / Launch Date | Status | Notes | Launch Status | Count
P1: Strategy & Plan (Pre-launch) | GTM Plan Development | Strategy |  |  | Marketing | PMM Lead |  |  |  |  | Align scope, audiences, launch goals and decision owners | COMPLETE
| Market Opportunity & Category Review | Research |  |  | Marketing | Market Insights | [5 empty] | In Progress
| Competitive Analysis | Research |  |  | Marketing | PMM Lead | [5 empty] | Not Started
| Validate ICP & Buyer Personas | Strategy |  | X | Marketing | PMM Lead | [5 empty] | At Risk
| Launch Goals & KPI Definition | Strategy |  |  | Marketing | Marketing Ops
| Budget Allocation | Strategy |  |  | Marketing | Demand Gen Lead
| Messaging & Positioning | Strategy |  |  | Marketing | PMM Lead
| Value Proposition | Strategy |  |  | Marketing | PMM Lead
| Priority Use Cases | Strategy |  | X | Marketing | PMM Lead
| Pricing & Packaging Review | Strategy |  | X | Product/Finance | Product Lead
| Customer Validation Interviews | Research |  | X | Marketing/Product | Research Lead
| Launch Readiness Review | Strategy |  |  | Cross-functional | GTM Lead
P2: Launch Readiness & Activation (Launch) | Product Naming & Narrative | Marketing - Content | X |  | Marketing | PMM Lead |  |  |  |  | Finalize launch narrative and product naming
| Product Overview Datasheet | Marketing - Content | X |  | Marketing | Content Lead
| Use-Case Datasheets | Marketing - Content | X | X | Marketing | Content Lead
| Sales Deck | Sales Support | X |  | Marketing | PMM Lead
| Sales Training Materials | Sales Prep |  |  | Marketing | PMM Lead
| Competitive Battlecards | Sales Support |  |  | Marketing | PMM Lead
| Sales Training & Certification | Sales Prep |  |  | Sales/Marketing | Enablement Lead
| BDR / SDR Playbook | Marketing - Outreach | X | X | Sales/Marketing | Demand Gen Lead
| Product Web Page | Marketing - Content | X |  | Marketing | Web Lead
| Use-Case Landing Pages | Marketing - Content | X | X | Marketing | Web Lead
| FAQ | Marketing - Content | X |  | Marketing | PMM Lead
| Launch Webinar | Marketing - Content | X |  | Marketing | Content Lead
| Launch Email 1 | Marketing - Outreach | X | X | Marketing | Lifecycle Lead
| Launch Blog Post | Marketing - Content | X |  | Marketing | Content Lead
| Paid Search Campaign | Marketing - Outreach | X | X | Marketing | Demand Gen Lead
| Retargeting Campaign | Marketing - Outreach | X |  | Marketing | Demand Gen Lead
| LinkedIn Campaign | Marketing - Outreach | X | X | Marketing | Demand Gen Lead
| Launch Email 2 | Marketing - Outreach | X | X | Marketing | Lifecycle Lead
| Executive Guide / eBook | Marketing - Content | X |  | Marketing | Content Lead
| Customer / Admin Onboarding Assets | Onboarding | X |  | Customer Success | CS Enablement
| Product Development & QA | Development |  |  | Product/Eng | Product Lead
| General Availability Launch | Launch | X |  | Cross-functional | GTM Lead
| Product Demo Video | Marketing - Content | X |  | Marketing | Video / Content
| Analyst / Influencer Briefings | PR / AR | X |  | Marketing | Comms Lead
P3: Tracking & Optimization (Post-launch) | Sales Win/Loss Review | Tracking |  |  | Marketing/Sales | PMM Lead |  |  |  |  | Identify message, product and competitive patterns
| Product Analytics Dashboard | Tracking |  |  | Product | Product Analytics
| Customer Feedback Program | Tracking |  |  | Customer Success | Customer Insights
| Pipeline & Funnel Review | Tracking |  |  | Marketing/Sales | Marketing Ops
| Adjust Messaging & Assets | Strategy | X | X | Marketing | PMM Lead
| Roadmap Input & Prioritization | Strategy |  |  | Product/Eng | Product Lead
| Customer Testimonials | Marketing - Content | X |  | Marketing/CS | Customer Marketing
| Reference & Advocacy Program | Marketing - Content | X |  | Marketing/CS | Customer Marketing
| Customer Case Study | Marketing - Content | X | X | Marketing | Content Lead